## Product Backlog
PRODUCT BACKLOG
Story ID | Product Backlog (stories) | Priority | Sprint # | Points | Acceptance Criteria
1 | As a customer, I want to electronically receive an invoice of my purchases so as to ensure the proper pricing and accounting of my goods. | 1 | 1 | 20 | The software system generates an electronic invoice of a customer's purchase and delivers it to their email.
2 | As a customer, I want to be able to initiate and process returns so as to obtain a refund or exchange items. | 1 | 1 | 20 | A refund/exchange request is electronically initiated by the customer and the firm receives the returned goods by an established and agreed-upon date.
3 | As a customer, I want to be able to browse through items and apply relevant filters so as to save time. | 1 | 1 | 40 | Items properly appear on the screen according to the sorting order specified by any applied filter. Otherwise, the most relevant product is displayed.
4 | As a customer, I want to be able to choose the most compatible payment method for my purchases. | 1 | 1 | 60 | Customers are shown all different forms of payment accepted, from apple pay to paypal.
5 | As a customer, I want to be able to modify my order by adding new products, changing or deleting products, and saving the modified order, so as to shop efficiently. | 1 | 1 | 40 | System correctly updates the order as requested by the customer in a smooth transaction.
6 | As a developer, I want to create an authentication and password management system so that the user can easily and securely register, log in, change or reset user name and password. | 1 | 1 | 70 | System registers new users, authenticates, and manages user accounts correctly and securely using two-factor authentication.
7 | As an administrator, I want to choose a vast collection of popular products to add to the inventory and modify product descriptions with up-to-date information if needed so that customers can easily find and purchase trending products knowing the latest information available to them. | 1 | 1 | 70 | System correctly adds products to the inventory, modifies, and updates product description and availability.
8 | As a user, I should be able to leave feedback to a product so that users can make a informed decision | 2 | 2 | 40 | System to add a verified customer tag to the review if the item is in user's purchase history
9 | As a user, I should be able to access possible shipping dates for the items in my cart. I should even have an option to change the shipping address before payment | 2 | 2 | 50 | Changing the shipping address should recalculate the delivery dates based on the nearest fullfillment center for the new address.
10 | As a admin, I should be able to manage seller information on the site | 2 | 2 | 20 | System stores all the data related to the sellers so that admins can access them to feed data into the inventory management system.
11 | As a user, I should be able to use alternative payment method such as gift cards/coupons, so that I can save money using promotions | 2 | 2 | 70 | System maintains information on all current promotions and matches them with the user's coupons/gift cards. If a match is found promotion discount is applied
12 | As a user, I should know the number of items available for purchase, so that I can make decide the number of items I can purchase. | 2 | 2 | 60 | System will get the inventory data from seller information and provide the maximum number of items that user can buy, if the items in cart exceeds the amount the order will be defaulted to the maximun amount.
13 | As a customer, I should be able to save products I wish to buy to an online shopping cart or wishlist. | 3 | 3 | 30 | System has a temporary list system that the user can use to keep track of saved products
14 | As a customer, I should be able to share a product on the website, to others online | 3 | 3 | 20 | Interface has an option to share directly to social media, as well as to generate links the user can copy and paste.
15 | As a customer I should be able to manage my personal profile as well as change my login information | 3 | 3 | 50 | System has the interface to change personal account setting and login information
16 | As a customer, I should be able to track a package that I have ordered | 3 | 3 | 40 | System provides a relavent tracking number that accurately refers to the delivery schedule
17 | As a customer I want to complain or need help/service | 4 | 3 | 20 | Representative should be assigned within particular time, able to identify an issue.
18 | As a customer, I want to see my past and cancelled orders | 4 | 3 | 20
19 | As a seller I want to list my products on store | 4 | 4 | 40 | System need to verify seller's id, list of products, products authenticity, tax informations etc.
20 | As a product owner, I want to maintain overall advertisement expenditure. | 4 | 4 | 20 | System should have advertisement platform account access, cost per click, targetted location information and graph layout implementation to display data interms to total spending, revenue and loss.
21 | As a customer, I want to view company policies regarding returns, exchanges, privacies etc. | 4 | 4 | 10 | System should have correct refund, return policies including which items are eligible for it. System also should have privacy and user data policy.
22 | As a customer, I would like so be able to shop via a mobile application so as to have a better shopping experience when making purchases through my phone or tablet. | 4 | 4 | 100 | Users are able to download the app on a mobile device and successfully access functionality comparable to the web-based version of the product.
23 | As a product owner, I want to manage advertisement expenditure so that I don't go overbudget. | 4 | 4 | 40 | System must display record of all advertisement purchases and show it on a document.

## Sprint Backlog
PRODUCT BACKLOG
SPRINT NO. 1
| Product Backlog Item | ID | Sprint Task | Volunteer | Initial Estimate of Effort | Distribution | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| As a customer, I want to electronically receive an invoice of my purchases so as to ensure the proper pricing and accounting of my goods. | 01 | Integrate completion of purchase with update of PO Info in the database | AH | 30 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Write script to pull PO info from database and format it | MV |  | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Create webpage with PO info | AF |  | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Create script to deliver embedded PO info with link to user email | WT |  | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Write test scripts | FK |  | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As a customer, I want to be able to initiate and process returns so as to obtain a refund or exchange items. | 02 | Create webpage for returns/exchanges | VK | 30 | 10 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add drop down menu for return reason | AH |  | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add clickable event to download return slip | MV |  | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Update order status in database | AF |  | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Create webpage for return status and summary | WT |  | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| As a customer, I want to be able to browse through items and apply relevant filters so as to save time. | 03 | Create drop-down menu for product filters | FK | 40 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add filter/display logic on the Front-End | VK |  | 20 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0
|  |  | Implement limit on amount of items displayed on page | AH |  | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add logic for creation of new pages if page limit is exceeded | MV |  | 10 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
| As a customer, I want to be able to choose the most compatible payment method for my purchases. | 04 | Set up preferences for payment methods using backend | AF | 60 | 20 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0
|  |  | Become familiar with credit card companies and their protocols for handling lost cards/fraud | WT |  | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
|  |  | Install credit card fraud prevention protocols | FK |  | 30 | 0 | 0 | 0 | 10 | 15 | 5 | 0 | 0 | 0 | 0
| As a customer, I want to be able to modify my order by adding new products, changing or deleting products, and saving the modified order, so as to shop efficiently. | 05 | Set up temporary memory cache to save orders | VK | 40 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0
|  |  | Install a feature to add a new product on website | AH |  | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0
|  |  | Install a feature to modify a product on website | MV |  | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0
|  |  | Install a feature to delete a product on websitel | AF |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
|  |  | Apply the latest modification | WT |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
| As a developer, I want to create an authentication and password management system so that the user can easily and securely register, log in, change or reset user name and password. | 06 | Set up database system for authentication | FK | 70 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 18 | 0 | 0
|  |  | Install user register module | VK |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0
|  |  | Install login module | AH |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0
|  |  | Install change user name and password module | MV |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0
|  |  | Install reset user name and password module | AF |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0
|  |  | Apply the latest modification | WT |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0
| As an administrator, I want to choose a vast collection of popular products to add to the inventory and modify product descriptions with up-to-date information if needed so that customers can easily find and purchase trending products knowing the latest information available to them. | 07 | Set up database system for all the products in the inventory | FK | 70 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 5
|  |  | Set up admin tools to manage inventory database | VK |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
|  |  | Install modify product description module | AH |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 15
7 |  |  | Install a feature that provides latest information about a product on website | MV |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 15
[5 empty] | Velocity = 340 |  | 15 | 20 | 30 | 40 | 50 | 32 | 15 | 38 | 45 | 55
SPRINT NO. 2
| Product Backlog Item | ID | Sprint Task | Volunteer | Initial Estimate of Effort | Distribution | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| As a customer, I want to be able to leave feedback for products so that users can make informed decisions. | 08 | Create display for reviews below product | AF | 40 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Update database schema to save reviews | WT |  | 20 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add clickable event to write review on product webpage | FK |  | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Implement sorting methods for reviews | VK |  | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
| As a customer, I want to be able to view possible shipping dates for the items in my cart, and have the option to change shipping address before payment, so that I can plan accordingly. | 09 | Create a product page for shipping dates | AH | 50 | 10 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
|  |  | Update the shipping dates value based on the address saved in the database schema | MV |  | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
|  |  | Add an option to change the shipping address before checkout | AF |  | 20 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0
|  |  | Implement the same to calculate all possible dates for the addresses saved in user profile. | WT |  | 15 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0
| As an admin, I want be able to manage seller information on the site so as to ensure accuracy. | 10 | Create a seller dashboard which only admins can access | FK | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
|  |  | Connect the dashboard to warehouse inventory database | VK |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
|  |  | Create a search option for admins to find the seller based on any meta data associated to seller's profile | AH |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
|  |  | Add the option for admins to contact the seller directly from the dashboard | MV |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
| As a customer, I want to be able to use alternative payment method such as gift cards/coupons so that I can save money. | 11 | Create a text space where coupons/giftcards can be added during check out. | AF | 70 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0
|  |  | Update database schema to store the payment methods provided. | WT |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 0
|  |  | Add a confirmation check to see if the promotional codes and coupons are valid by cross referencing the database. | FK |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
|  |  | Add a space for users to request admins to add other alternative payment methods that are not currently supported by the website. | VK |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| As a customer, I want to know the number of items available for purchase, so that I can decide whether to buy or not. | 12 | Create a dropdown on the product page that shows the maximum number of items that a user can add to cart | AH | 60 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15
|  |  | Connect the dropdown to database to check if seller provided a limit, if not default limit will be 10 items. | MV |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 15
|  |  | Add a event to check if the total number of items in the user's cart is less than or equal to specified limit. | AF |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
[5 empty] | Velocity = 240 |  | 5 | 5 | 15 | 20 | 40 | 20 | 30 | 30 | 45 | 30
SPRINT NO. 3
| Product Backlog Item | ID | Sprint Task | Volunteer | Initial Estimate of Effort | Distribution | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| As a customer, I want to be able to save products an online shopping cart of wishlist so as to make a purchase at a later time. | 13 | Create Wishlist to save items on furture site visits | WT | 30 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Create Shopping Cart that save only items in current session, but also immediate checkout | FK |  | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add button to add an item to either cart or wishlist from product page | VK |  | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
| As a customer, I want be able to share products found on the website with others so as to share my recommendations. | 14 | Add function to generate links to product page | AH | 20 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add function to share directly to social media | MV |  | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
|  |  | Add fucntion to share via SMS | AF |  | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
| As a customer, I want to be able to manage my personal so as to have greater flexibility profile and change my login information | 15 | Add function to access personal profile | WT | 50 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
|  |  | Add function to edit personal profile | FK |  | 15 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0
|  |  | Add fucnction to change username and password | VK |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
| As a customer, I should be able to track packages that I have ordered so as to stay informed about the status of my order. | 16 | Add system to assign tracking number | AH | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0
|  |  | Add system to track packages via shipping updates | MV |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
|  |  | Add system to indicate when a package is delivered | AF |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
| As a customer, I want to be able to chat with a virtual interface so as to get assistance with my questions. | 17 | Add system to get all user's data and offer most frequently asked questions and services | WT | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0
|  |  | Add system to offer virtual chat box | FK |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
| As a customer, I want to be able to see my past and cancelled orders so as to keep track of items purchased. | 18 | Add system to display all previous orders from database | VK | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
[5 empty] | Velocity = 180 |  | 5 | 5 | 10 | 20 | 20 | 10 | 30 | 30 | 20 | 30
SPRINT NO. 4
| Product Backlog Item | ID | Sprint Task | Volunteer | Initial Estimate of Effort | Distribution | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| As a seller, I want to be able to list my products on the store website/catalog so as to generate revenue. | 19 | Create 'Vendor Account' as a User type in the database | AH | 40 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Create tab and webpage allowing users to type info for listings | MV |  | 20 | 5 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Add logic to be able to save a listing into the database | AF |  | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
| As a product owner, I want to to be able to track advertisement expenditures so as to make effective use of funds | 20 | Create tab and webpage for showing advertisement metrics | WT | 25 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Restrict access to this tab/wepage | FK |  | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | link wepage to advertisements API | VK |  | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
| As a customer, I want to view company policies regarding returns, exchanges, privacies etc. | 21 | Add tab for company policies and drop-down menu for specific topics | AH | 10 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
|  |  | Create seperate webpages for different policy sections | MV |  | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
|  |  | Add naviation hyperlinks | AF |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| As a customer, I would like so be able to shop via a mobile application so as to have a better shopping experience when making purchases through my phone or tablet. | 22 | Develop front-end UI | WT | 100 | 40 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 15 | 0 | 0
|  |  | Set-up access to database | FK |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
|  |  | Set-up for App deployment | VK |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 0 | 0
|  |  | Write automated integration tests | AH |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 5 | 0
|  |  | Set-up distribution and publishing on App stores | MV |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5
23 | As a product owner, I want to manage advertisement expenditure so that I don't go overbudget. | 23 | Create excel and log all expenses | AF | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 5
|  |  | Build a function that notifies team if expenses get close to budgeted amount | WT |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
[5 empty] | Velocity = 215 |  | 10 | 5 | 10 | 30 | 20 | 10 | 40 | 30 | 30 | 30

## Task Sign-up
TASK SIGN-UP
Task | Priority | Accepted date | Assigned to
Product Backlog S1 | 1 | 2022-02-23 | AH
Product Backlog S2 | 1 | 2022-02-23 | AH
Product Backlog S3 | 1 | 2022-02-25 | AH
Product Backlog S4 | 1 | 2022-02-25 | WT
Product Backlog S5 | 1 | 2022-02-23 | FK
Product Backlog S6 | 1 | 2022-02-25 | FK
Product Backlog S7 | 1 | 2022-02-25 | FK
Product Backlog S8 | 1 | 2022-02-23 | VK
Product Backlog S9 | 1 | 2022-02-23 | VK
Product Backlog S10 | 1 | 2022-02-23 | VK
Product Backlog S11 | 1 | 2022-02-23 | VK
Product Backlog S12 | 1 | 2022-02-23 | VK
Product Backlog S13 | 1 | 2022-02-25 | AF
Product Backlog S14 | 1 | 2022-02-25 | AF
Product Backlog S15 | 1 | 2022-02-25 | AF
Product Backlog S16 | 1 | 2022-02-25 | AF
Product Backlog S17 | 1 | 2022-02-25 | MV
Product Backlog S18 | 1 | 2022-02-25 | MV
Product Backlog S19 | 1 | 2022-02-25 | MV
Product Backlog S20 | 1 | 2022-02-25 | MV
Product Backlog S21 | 1 | 2022-02-25 | MV
Product Backlog S22 | 1 | 2022-02-25 | AH
Product Backlog S23 | 1 | 2022-02-25 | WT
VS Doc 1.1 | 2 | 2022-02-23 | AH
VS Doc 1.2 | 2 | 2022-02-23 | AH
VS Doc 1.3 | 2 | 2022-02-23 | AH
VS Doc 1.4 | 2 | 2022-02-23 | FK
VS Doc 1.5 | 2 | 2022-02-23 | FK
VS Doc 1.6 | 2 | 2022-02-23 | FK
VS Doc 1.7 | 2 | 2022-02-25 | MV
VS Doc 2.1 | 2 | 2022-02-23 | WT
VS Doc 2.2 | 2 | 2022-02-23 | WT
VS Doc 2.3 | 2 | 2022-02-23 | WT
VS Doc 2.4 | 2 | 2022-02-25 | AF
VS Doc 3.1 | 2 | 2022-02-25 | AF
VS Doc 3.2 | 2 | 2022-02-25 | AF
VS Doc 3.3 | 2 | 2022-02-25 | MV
Product Backlog Points S1-S7 |  | 2022-02-28 | All
Product Backlog Points Rest |  | 2022-03-01 | VK
Sprint Backlog 1.1 |  | 2022-03-04 | AH
Sprint Backlog 1.2 |  | 2022-03-04 | AH
Sprint Backlog 1.3 |  | 2022-03-04 | AH
Sprint Backlog 1.4 |  | 2022-03-04 | WT
Sprint Backlog 1.5 |  | 2022-03-04 | FK
Sprint Backlog 1.6 |  | 2022-03-04 | FK
Sprint Backlog 1.7 |  | 2022-03-04 | FK
Sprint Backlog 2.8 |  | 2022-03-04 | AH
Sprint Backlog 2.9 |  | 2022-03-04 | VK
Sprint Backlog 2.10 |  | 2022-03-04 | VK
Sprint Backlog 2.11 |  | 2022-03-04 | VK
Sprint Backlog 2.12 |  | 2022-03-04 | VK
Sprint Backlog 3.13 |  | 2022-03-04 | MV
Sprint Backlog 3.14 |  | 2022-03-04 | MV
Sprint Backlog 3.15 |  | 2022-03-04 | MV
Sprint Backlog 3.16 |  | 2022-03-04 | MV
Sprint Backlog 3.17 |  | 2022-03-04 | MV
Sprint Backlog 3.18 |  | 2022-03-04 | MV
Sprint Backlog 4.19 |  | 2022-03-04 | AH
Sprint Backlog 4.20 |  | 2022-03-04 | AH
Sprint Backlog 4.21 |  | 2022-03-04 | AH
Sprint Backlog 4.22 |  | 2022-03-04 | AH
Sprint Backlog 4.23 |  | 2022-03-04 | WT
Burn-down Chart S1 |  | 2022-03-11 | FK
Burn-down Chart S2 |  | 2022-03-11 | FK
Burn-down Chart S3 |  | 2022-03-11 | FK
Burn-down Chart S4 |  | 2022-03-11 | FK

## Closed Tasks
CLOSED TASKS
Task | Priority | Acceptance Date | Assigned to | Completion Date
Product Backlog S1 | 1 | 2022-02-23 | AH | 2022-02-25
Product Backlog S2 | 1 | 2022-02-23 | AH | 2022-02-25
Product Backlog S3 | 1 | 2022-02-25 | AH | 2022-02-25
Product Backlog S4 | 1 | 2022-02-25 | WT | 2022-02-28
Product Backlog S5 | 1 | 2022-02-23 | FK | 2022-02-25
Product Backlog S6 | 1 | 2022-02-25 | FK | 2022-02-27
Product Backlog S7 | 1 | 2022-02-25 | FK | 2022-02-27
Product Backlog S8 | 1 | 2022-02-23 | VK | 2022-02-25
Product Backlog S9 | 1 | 2022-02-23 | VK | 2022-02-25
Product Backlog S10 | 1 | 2022-02-23 | VK | 2022-02-25
Product Backlog S11 | 1 | 2022-02-23 | VK | 2022-02-25
Product Backlog S12 | 1 | 2022-02-23 | VK | 2022-02-25
Product Backlog S13 | 1 | 2022-02-25 | AF | 2022-02-25
Product Backlog S14 | 1 | 2022-02-25 | AF | 2022-02-25
Product Backlog S15 | 1 | 2022-02-25 | AF | 2022-02-25
Product Backlog S16 | 1 | 2022-02-25 | AF | 2022-02-25
Product Backlog S17 | 1 | 2022-02-25 | MV | 2022-02-25
Product Backlog S18 | 1 | 2022-02-25 | MV | 2022-02-25
Product Backlog S19 | 1 | 2022-02-25 | MV | 2022-02-25
Product Backlog S20 | 1 | 2022-02-25 | MV | 2022-02-25
Product Backlog S21 | 1 | 2022-02-25 | MV | 2022-02-25
Product Backlog S22 | 1 | 2022-02-25 | AH | 2022-02-26
Product Backlog S23 | 1 | 2022-02-25 | WT | 2022-02-28
VS Doc 1.1 | 2 | 2022-02-23 | AH | 2022-03-03
VS Doc 1.2 | 2 | 2022-02-23 | AH | 2022-03-03
VS Doc 1.3 | 2 | 2022-02-23 | AH | 2022-03-03
VS Doc 1.4 | 2 | 2022-02-23 | FK | 2022-02-28
VS Doc 1.5 | 2 | 2022-02-23 | FK | 2022-02-28
VS Doc 1.6 | 2 | 2022-02-23 | FK | 2022-02-28
VS Doc 1.7 | 2 | 2022-02-25 | MV | 2022-03-03
VS Doc 2.1 | 2 | 2022-02-23 | WT | 2022-02-28
VS Doc 2.2 | 2 | 2022-02-23 | WT | 2022-02-28
VS Doc 2.3 | 2 | 2022-02-23 | WT | 2022-02-28
VS Doc 2.4 | 2 | 2022-02-25 | AF | 2022-03-11
VS Doc 3.1 | 2 | 2022-02-25 | AF | 2022-03-11
VS Doc 3.2 | 2 | 2022-02-25 | AF | 2022-03-11
VS Doc 3.3 | 2 | 2022-02-25 | MV | 2022-03-03
Product Backlog Points S1-S7 |  | 2022-02-28 | All | 2022-03-07
Product Backlog Points Rest |  | 2022-03-01 | VK | 2022-03-07
Sprint Backlog 1.1 |  | 2022-03-04 | AH | 2022-03-04
Sprint Backlog 1.2 |  | 2022-03-04 | AH | 2022-03-04
Sprint Backlog 1.3 |  | 2022-03-04 | AH | 2022-03-04
Sprint Backlog 1.4 |  | 2022-03-04 | WT | 2022-03-07
Sprint Backlog 1.5 |  | 2022-03-04 | FK | 2022-03-06
Sprint Backlog 1.6 |  | 2022-03-04 | FK | 2022-03-06
Sprint Backlog 1.7 |  | 2022-03-04 | FK | 2022-03-06
Sprint Backlog 2.8 |  | 2022-03-04 | AH | 2022-03-05
Sprint Backlog 2.9 |  | 2022-03-04 | VK | 2022-03-06
Sprint Backlog 2.10 |  | 2022-03-04 | VK | 2022-03-06
Sprint Backlog 2.11 |  | 2022-03-04 | VK | 2022-03-08
Sprint Backlog 2.12 |  | 2022-03-04 | VK | 2022-03-08
Sprint Backlog 3.13 |  | 2022-03-04 | MV | 2022-03-07
Sprint Backlog 3.14 |  | 2022-03-04 | MV | 2022-03-07
Sprint Backlog 3.15 |  | 2022-03-04 | MV | 2022-03-09
Sprint Backlog 3.16 |  | 2022-03-04 | MV | 2022-03-09
Sprint Backlog 3.17 |  | 2022-03-04 | MV | 2022-03-09
Sprint Backlog 3.18 |  | 2022-03-04 | MV | 2022-03-10
Sprint Backlog 4.19 |  | 2022-03-04 | AH | 2022-03-04
Sprint Backlog 4.20 |  | 2022-03-04 | AH | 2022-03-04
Sprint Backlog 4.21 |  | 2022-03-04 | AH | 2022-03-04
Sprint Backlog 4.22 |  | 2022-03-04 | AH | 2022-03-04
Sprint Backlog 4.23 |  | 2022-03-04 | WT | 2022-03-07
Burn-down Chart S1 |  | 2022-03-11 | FK | 2022-03-11
Burn-down Chart S2 |  | 2022-03-11 | FK | 2022-03-11
Burn-down Chart S3 |  | 2022-03-11 | FK | 2022-03-11
Burn-down Chart S4 |  | 2022-03-11 | FK | 2022-03-11